## Sheet1
Risk ID | Risk Description | Likelihood (1–9) | Impact (1–9)
R01 | Violation of GDPR compliance requirements in the EU | 5 | 9
R02 | Data localization non-compliance in India | 6 | 8
R03 | Failure to manage encryption integration securely | 7 | 5
R04 | Conflict between WhatsApp's privacy model and Amazon's data usage | 7 | 7
R05 | Negative user reaction to monetization strategies | 7 | 8
R06 | Delayed regulatory approval in emerging markets | 4 | 6
R07 | Integration latency between WhatsApp and AWS | 4 | 9
R08 | Increased operational costs due to compliance adaptation | 9 | 9
R09 | Lack of skilled personnel in encrypted communications | 6 | 7
R10 | Cross-functional misalignment in implementation teams | 9 | 6
R11 | Reduced engagement due to design incompatibility | 5 | 6
R12 | Failure of AI recommendation systems on WhatsApp | 4 | 5
R13 | Public backlash over cross-platform data sharing | 6 | 7
R14 | Security audit failure post-integration | 4 | 8
R15 | Drop in brand trust from mismanaged privacy disclosures | 8 | 6
R16 | Legal disputes with telecom providers in foreign markets | 8 | 5
R17 | High infrastructure cost to support new traffic volume | 7 | 5
R18 | Political resistance in authoritarian-regime countries | 4 | 7
R19 | Internal employee turnover in WhatsApp post-acquisition | 9 | 9
R20 | Stakeholder disagreement over post-merger goals | 4 | 6